🚀 PROJECT NAME: “Neon Rush” – Energy Drink Soft Launch (Phase 1??)
(Internal Ref: MRKT-Q1-NEON)

Brand / Client: PulseWave Beverages
Product: Neon Rush – Zero Sugar Energy Drink
Region Focus: Tier 1 Cities (NYC, LA, Chicago) + test market in Austin

🎯 TARGET (Not Final – Needs Validation)

- Age Range: 18–35 (maybe extend to 40 depending on TikTok performance)

- Audience Types:

  - Gamers (PC + Console)

  - Night-shift workers

  - Fitness enthusiasts (early morning crowd)

- Behavior:

  - Heavy social media usage

  - Late-night consumption patterns

💬 CORE MESSAGE IDEAS (pick 1 or hybrid)

- “Power Past Midnight”

- “Zero Sugar. Maximum Charge.”

- “Stay Lit Without the Crash”

⚠ Might need A/B testing across platforms.

📅 TIMELINE (Tentative)

- Creative Draft Deadline → Feb 10, 2026

- Internal Review → Feb 13–15

- Soft Launch → Feb 18

- Full Campaign Push → March 1

NOTE: Influencer contracts may delay rollout by 3–5 days.

📊 KPIs / SUCCESS METRICS

Primary:

- App installs: 20K

- Email signups: 12K
Secondary:

- CTR > 2.8%

- Video Completion Rate > 35%
Stretch Goal:

- 5% conversion from landing page traffic

💰 BUDGET BREAKDOWN (Approx.)

Total Budget: $75,000

- Influencers → $28,000

- Paid Ads → $32,000

- Creative Production → $10,000

- Contingency Buffer → $5,000

(Still waiting on finance approval)

🎨 CREATIVE DIRECTION (Rough Notes)

- Visual Style:

  - Neon colors (purple + cyan preferred)

  - Dark backgrounds

  - Motion blur effects

- Must Include:

  - Product can close-up

  - Energy pulse animation

  - Sound effects for TikTok/Reels

Avoid:

- “Gym bro” stereotypes

- Overused lightning effects

📢 CHANNEL PLAN

Priority:

- TikTok (Short-form video)

- Instagram Reels
Secondary:

- YouTube Shorts

- Twitch pre-roll ads (experimental)

📎 DELIVERABLES LIST (Draft)

- 6 short-form videos (15–30 sec)

- 4 static ad creatives

- 2 landing page hero banners

- Email header design

👥 CONTACTS / OWNERS

Marketing Lead: Jason Reed
Email: j.reed@pulsewavebev.com
Phone: +1-555-884-2211

Creative Manager: Lina Torres
Slack: @lina.creative

⚠ OPEN ISSUES / TO-DO

- Finalize slogan

- Confirm influencer shortlist

- Legal approval for health claims

- Update packaging mockups

- Landing page copy still missing